## 2.2 Totex costs summary
Regulatory Reporting Pack
Cadent West Midlands
2016/17
2.2 Summary of totex costs
Current year RRP submission - £m
2016/17 prices
| Actuals |  |  | Current year actuals | Forecast |  |  |  | Forecast RIIO Total
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
LTS, storage and entry | 4.4385 | 6.292 | 2.4472 | 5.0378 | 5.3105 | 5.0385 | 4.4126 | 4.9067 | 37.8837
Connections | 4.8599 | 5.3758 | 6.7269 | 4.8213 | 5.9237 | 5.6987 | 5.5752 | 5.5172 | 44.4987
Mains Reinforcement | 0.80335 | 0.17372 | 0.40591 | 0.65205 | 0.9355 | 0.9 | 0.95 | 1 | 5.8205
Governors (Replacement) | 0.69378 | 0.54457 | 0.57182 | 0.64055 | 1.6439 | 1.6689 | 1.6622 | 1.7105 | 9.1362
Other Capex | 11.64 | 11.6396 | 9.214 | 10.1811 | 8.6797 | 8.2146 | 9.7874 | 9.8595 | 79.216
of which IT | 7.1802 | 5.8741 | 4.3853 | 2.601 | 1.167 | 1.167 | 2.973 | 2.973 | 28.3207
of which Vehicles | 1.7816 | 1.1584 | 1.4137 | 2.9896 | 2.8706 | 1.9689 | 1.5776 | 1.202 | 14.9624
Total Capex | 22.4356 | 24.0257 | 19.3658 | 21.3329 | 22.4932 | 21.5207 | 22.3873 | 22.9939 | 176.5552
HSE driven mains & services | 57.9016 | 44.9699 | 66.6205 | 57.4715 | 51.2219 | 51.4182 | 51.4182 | 51.1122 | 432.1339
Non-HSE driven mains & services | 5.5566 | 8.2223 | 14.0095 | 14.5351 | 14.5109 | 10.7545 | 9.0585 | 7.6416 | 84.289
Risers | 0.30586 | 1.6545 | 2.0271 | 0.65921 | 0.9733 | 0.80978 | 0.81361 | 0.83072 | 8.0741
Total Repex | 63.7641 | 54.8467 | 82.6571 | 72.6658 | 66.7061 | 62.9825 | 61.2903 | 59.5845 | 524.4971
Work Management | 25.6379 | 20.0349 | 18.9102 | 18.6209 | 18.8298 | 18.1429 | 17.1686 | 16.7852 | 154.1305
Emergency | 8.7077 | 9.0939 | 8.5275 | 8.5466 | 9.6259 | 9.8231 | 10.2284 | 9.9792 | 74.5322
Repair | 10.3709 | 10.3769 | 9.1945 | 10.7283 | 10.2032 | 9.9771 | 9.5361 | 9.4064 | 79.7933
Maintenance | 8.2414 | 9.3702 | 10.2413 | 11.2683 | 13.3062 | 12.4555 | 12.7807 | 10.7333 | 88.3967
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 |  |  |  |  | 0
Other Direct Activities | 5.9223 | 6.1999 | 6.1129 | 5.3291 | 5.2225 | 4.5829 | 4.5811 | 4.5767 | 42.5273
of which xoserve | 3.3591 | 3.7227 | 3.4436 | 2.9799 | 2.6476 | 2.0933 | 2.0933 | 2.0933 | 22.4327
Total Direct Opex | 58.8802 | 55.0757 | 52.9864 | 54.4931 | 57.1876 | 54.9815 | 54.2948 | 51.4808 | 439.3801
Business support | 22.7699 | 22.7341 | 21.2636 | 20.5005 | 22.7721 | 21.9824 | 19.9629 | 18.6674 | 170.6529
Training & Apprentices | 1.4894 | 1.2213 | 1.7846 | 2.7655 | 3.772 | 3.4794 | 3.1643 | 2.9168 | 20.5933
Total Indirect Opex | 24.2592 | 23.9554 | 23.0482 | 23.2661 | 26.5441 | 25.4618 | 23.1273 | 21.5842 | 191.2463
Total Opex | 83.1394 | 79.0312 | 76.0346 | 77.7592 | 83.7317 | 80.4433 | 77.422 | 73.065 | 630.6263
Of which total sub-deducts | 0.27629 | 0.00044945 | 0.080144 | 0.12729 | 0 | 0 | 0 | 0
Total Controllable costs | 169.3391 | 157.9036 | 178.0575 | 171.7579 | 172.9309 | 164.9465 | 161.0997 | 155.6434 | 1331.6787
Non-Controllable costs
Licence/network/other | 29.5729 | 32.1094 | 31.7052 | 32.571 | 44.3693 | 43.4703 | 43.4688 | 43.469 | 300.7358
NTS exit costs | 21.4903 | 20.8221 | 19.8623 | 20.8333 | 21.6329 | 17.8174 | 21.7401 | 20.7737 | 164.9721
Shrinkage | 7.2817 | 5.0932 | 3.8533 | 3.6823 | 3.7441 | 3.7617 | 3.7804 | 3.7952 | 34.9919
NTS pensions contributions | 3.9222 | 3.9813 | 5.5237 | 5.4359 | 3.3944 | 3.3944 | 0 | 0 | 25.6519
Total non-controllable costs | 62.2671 | 62.006 | 60.9445 | 62.5224 | 73.1407 | 68.4439 | 68.9893 | 68.038 | 526.3518
Total funded costs - including uncertainties | 231.6062 | 219.9096 | 239.002 | 234.2803 | 246.0716 | 233.3904 | 230.089 | 223.6813 | 1858.0305
Of which: uncertainties*:
Smart metering | 0.096951 | 0.18291 | 0.30061 | 0.5864 | 3.211 | 4.2802 | 2.6683 | 2.5058 | 13.8322
Streetworks | 0.89477 | 1.3454 | 1.1643 | 1.6993 | 0 | 0 | 0 | 0 | 5.1037
Physical Security Upgrade Programme (PSUP) | -0.12873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.12873
Statutory independent undertakings (SIUs) | - | - | - | 0 | 0 | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total uncertainties* | 0.86299 | 1.5283 | 1.4649 | 2.2857 | 3.211 | 4.2802 | 2.6683 | 2.5058 | 18.8071
Total funded costs - excluding uncertainties* | 230.7432 | 218.3813 | 237.5372 | 231.9946 | 242.8606 | 229.1102 | 227.4207 | 221.1755 | 1839.2233
Previous year RRP submission - £m | [10 empty] | Variance from previous year | [9 empty] | % Variance from previous year
2016/17 prices
| Actuals |  |  | Forecast
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
LTS, storage and entry | 4.4385 | 6.292 | 2.4472 | 4.1136 | 5.3105 | 5.0385 | 4.4126 | 4.9067 | 36.9596 |  | LTS, storage and entry | 0 | 0 | 0 | 0.92416 | 0 | 0 | 0 | 0 | 0.92416 | LTS, storage and entry | 0% | 0% | 0% | 22.47% | 0% | 0% | 0% | 0% | 2.5%
Connections | 4.8599 | 5.3758 | 6.7269 | 4.6326 | 4.8669 | 4.8489 | 4.6687 | 4.5425 | 40.5223 |  | Connections | 0 | 0 | 0 | 0.1887 | 1.0568 | 0.84976 | 0.90651 | 0.97475 | 3.9765 | Connections | 0% | 0% | 0% | 4.073% | 21.71% | 17.52% | 19.42% | 21.46% | 9.813%
Mains Reinforcement | 0.80335 | 0.17372 | 0.40591 | 0.32639 | 1.0909 | 1.1491 | 2.1797 | 2.1797 | 8.3088 |  | Mains Reinforcement | 0 | 0 | 0 | 0.32566 | -0.15538 | -0.2491 | -1.2297 | -1.1797 | -2.4883 | Mains Reinforcement | 0% | 0% | 0% | 99.78% | -14.24% | -21.68% | -56.42% | -54.12% | -29.95%
Governors (Replacement) | 0.69378 | 0.54457 | 0.57182 | 0.56368 | 1.6439 | 1.6689 | 1.6622 | 1.7105 | 9.0593 |  | Governors (Replacement) | 0 | 0 | 0 | 0.076871 | 0 | 0 | 0 | 0 | 0.076871 | Governors (Replacement) | 0% | 0% | 0% | 13.64% | 0% | 0% | 0% | 0% | 0.8485%
Other Capex | 11.64 | 11.6396 | 9.214 | 9.1892 | 8.3287 | 9.0377 | 10.8684 | 11.0111 | 80.9288 |  | Other Capex | 0 | 0 | 0 | 0.99197 | 0.35094 | -0.82309 | -1.081 | -1.1516 | -1.7128 | Other Capex | 0% | 0% | 0% | 10.79% | 4.214% | -9.107% | -9.946% | -10.46% | -2.116%
of which IT | 7.1802 | 5.8741 | 4.3853 | 2.5577 | 1.167 | 1.167 | 2.973 | 2.973 | 28.2774 |  | of which IT | 0 | 0 | 0 | 0.043352 | 0 | 0 | 0 | 0 | 0.043352 | of which IT | 0% | 0% | 0% | 1.695% | 0% | 0% | 0% | 0% | 0.1533%
of which Vehicles | 1.7816 | 1.1584 | 1.4137 | 1.536 | 2.0706 | 1.9689 | 1.5776 | 1.202 | 12.7088 |  | of which Vehicles | 0 | 0 | 0 | 1.4536 | 0.8 | -1.7764e-15 | 0 | 0 | 2.2536 | of which Vehicles | 0% | 0% | 0% | 94.64% | 38.64% | -9.022e-14% | 0% | 0% | 17.73%
Total Capex | 22.4356 | 24.0257 | 19.3658 | 18.8255 | 21.2409 | 21.7432 | 23.7915 | 24.3505 | 175.7787 |  | Total Capex | 0 | 0 | 0 | 2.5074 | 1.2523 | -0.22243 | -1.4042 | -1.3566 | 0.77649 | Total Capex | 0% | 0% | 0% | 13.32% | 5.896% | -1.023% | -5.902% | -5.571% | 0.4417%
HSE driven mains & services | 57.9016 | 44.9699 | 66.6205 | 61.2942 | 53.783 | 49.9804 | 48.1127 | 46.8349 | 429.4972 |  | HSE driven mains & services | 0 | 0 | 0 | -3.8227 | -2.5611 | 1.4378 | 3.3055 | 4.2773 | 2.6367 | HSE driven mains & services | 0% | 0% | 0% | -6.237% | -4.762% | 2.877% | 6.87% | 9.133% | 0.6139%
Non-HSE driven mains & services | 5.5566 | 8.2223 | 14.0095 | 9.2177 | 9.9498 | 10.844 | 11.0158 | 10.5706 | 79.3863 |  | Non-HSE driven mains & services | 0 | 0 | 0 | 5.3174 | 4.5611 | -0.089501 | -1.9572 | -2.929 | 4.9028 | Non-HSE driven mains & services | 0% | 0% | 0% | 57.69% | 45.84% | -0.8253% | -17.77% | -27.71% | 6.176%
Multi occupancy buildings (MoBs) | 0.30586 | 1.6545 | 2.0271 | 0.55489 | 0.9733 | 0.80978 | 0.81361 | 0.83072 | 7.9698 |  | Multi occupancy buildings (MoBs) | 0 | 0 | 0 | 0.10432 | 0 | 0 | 0 | 0 | 0.10432 | Multi occupancy buildings (MoBs) | 0% | 0% | 0% | 18.8% | 0% | 0% | 0% | 0% | 1.309%
Total Repex | 63.7641 | 54.8467 | 82.6571 | 71.0668 | 64.7061 | 61.6342 | 59.9421 | 58.2362 | 516.8533 |  | Total Repex | 0 | 0 | 0 | 1.599 | 2 | 1.3483 | 1.3483 | 1.3483 | 7.6438 | Total Repex | 0% | 0% | 0% | 2.25% | 3.091% | 2.188% | 2.249% | 2.315% | 1.479%
Work Management | 25.6379 | 20.0349 | 18.9102 | 19.3757 | 18.8935 | 18.6215 | 17.6374 | 17.2606 | 156.3716 |  | Work Management | 0 | 0 | 0 | -0.75475 | -0.063613 | -0.47852 | -0.46885 | -0.4754 | -2.2411 | Work Management | 0% | 0% | 0% | -3.895% | -0.3367% | -2.57% | -2.658% | -2.754% | -1.433%
Emergency | 8.7077 | 9.0939 | 8.5275 | 9.6652 | 10.0201 | 10.6323 | 10.8728 | 10.6036 | 78.1231 |  | Emergency | 0 | 0 | 0 | -1.1187 | -0.39418 | -0.80922 | -0.64439 | -0.62436 | -3.5908 | Emergency | 0% | 0% | 0% | -11.57% | -3.934% | -7.611% | -5.927% | -5.888% | -4.596%
Repair | 10.3709 | 10.3769 | 9.1945 | 10.8178 | 10.7809 | 11.0374 | 10.3316 | 10.1828 | 83.0928 |  | Repair | 0 | 0 | 0 | -0.089518 | -0.57766 | -1.0603 | -0.79553 | -0.77643 | -3.2995 | Repair | 0% | 0% | 0% | -0.8275% | -5.358% | -9.607% | -7.7% | -7.625% | -3.971%
Maintenance | 8.2414 | 9.3702 | 10.2413 | 11.0641 | 13.5744 | 13.1438 | 13.4944 | 11.4286 | 90.5581 |  | Maintenance | 0 | 0 | 0 | 0.20414 | -0.26824 | -0.68831 | -0.71369 | -0.69527 | -2.1614 | Maintenance | 0% | 0% | 0% | 1.845% | -1.976% | -5.237% | -5.289% | -6.084% | -2.387%
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | - | - | - | - | - | - | - | - | -
Other Direct Activities | 5.9223 | 6.1999 | 6.1129 | 7.455 | 5.7629 | 5.5142 | 5.5907 | 5.5142 | 48.072 |  | Other Direct Activities | 0 | 0 | 0 | -2.1259 | -0.54042 | -0.93125 | -1.0096 | -0.93747 | -5.5447 | Other Direct Activities | 0% | 0% | 0% | -28.52% | -9.378% | -16.89% | -18.06% | -17% | -11.53%
of which xoserve | 3.3591 | 3.7227 | 3.4436 | 4.835 | 3.1677 | 2.9226 | 2.998 | 2.9226 | 27.3711 |  | of which xoserve | 0 | 0 | 0 | -1.8551 | -0.52008 | -0.82928 | -0.9047 | -0.82928 | -4.9384 | of which xoserve | 0% | 0% | 0% | -38.37% | -16.42% | -28.37% | -30.18% | -28.37% | -18.04%
Total Direct Opex | 58.8802 | 55.0757 | 52.9864 | 58.3778 | 59.0317 | 58.9491 | 57.9269 | 54.9897 | 456.2176 |  | Total Direct Opex | 0 | 0 | 0 | -3.8847 | -1.8441 | -3.9676 | -3.6321 | -3.5089 | -16.8375 | Total Direct Opex | 0% | 0% | 0% | -6.654% | -3.124% | -6.731% | -6.27% | -6.381% | -3.691%
Business support | 22.7699 | 22.7341 | 21.2636 | 21.0368 | 20.5877 | 20.6616 | 20.2073 | 19.8782 | 169.1392 |  | Business support | 0 | 0 | 0 | -0.53626 | 2.1844 | 1.3208 | -0.24439 | -1.2108 | 1.5137 | Business support | 0% | 0% | 0% | -2.549% | 10.61% | 6.393% | -1.209% | -6.091% | 0.895%
Training & Apprentices | 1.4894 | 1.2213 | 1.7846 | 3.2049 | 3.2714 | 2.9788 | 2.6638 | 2.4162 | 19.0305 |  | Training & Apprentices | 0 | 0 | 0 | -0.43939 | 0.50057 | 0.50057 | 0.50057 | 0.50057 | 1.5629 | Training & Apprentices | 0% | 0% | 0% | -13.71% | 15.3% | 16.8% | 18.79% | 20.72% | 8.213%
Total Indirect Opex | 24.2592 | 23.9554 | 23.0482 | 24.2417 | 23.8591 | 23.6404 | 22.8711 | 22.2944 | 188.1696 |  | Total Indirect Opex | 0 | 0 | 0 | -0.97565 | 2.6849 | 1.8214 | 0.25618 | -0.71024 | 3.0766 | Total Indirect Opex | 0% | 0% | 0% | -4.025% | 11.25% | 7.705% | 1.12% | -3.186% | 1.635%
Total Opex | 83.1394 | 79.0312 | 76.0346 | 82.6195 | 82.8909 | 82.5895 | 80.798 | 77.2841 | 644.3872 |  | Total Opex | 0 | 0 | 0 | -4.8603 | 0.84082 | -2.1462 | -3.3759 | -4.2192 | -13.7608 | Total Opex | 0% | 0% | 0% | -5.883% | 1.014% | -2.599% | -4.178% | -5.459% | -2.135%
Total sub-deducts | 0.27629 | 0.00044945 | 0.080144 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total sub-deducts | [9 empty] | Total sub-deducts | 0% | 0% | 0%
Total Controllable costs | 169.3391 | 157.9036 | 178.0575 | 172.5118 | 168.8378 | 165.9669 | 164.5315 | 159.8709 | 1337.0192 |  | Total Controllable costs | 0 | 0 | 0 | -0.75395 | 4.0931 | -1.0204 | -3.4318 | -4.2275 | -5.3405 | Total Controllable costs | 0% | 0% | 0% | -0.437% | 2.424% | -0.6148% | -2.086% | -2.644% | -0.3994%
Non-Controllable costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Non-Controllable costs | [9 empty] | Non-Controllable costs
Licence/network/other | 29.5729 | 32.1094 | 31.7052 | 33.1765 | 33.4197 | 33.5648 | 34.2382 | 34.0069 | 261.7936 |  | Licence/network/other | 0 | 0 | 0 | -0.60552 | 10.9496 | 9.9055 | 9.2306 | 9.4621 | 38.9422 | Licence/network/other | 0% | 0% | 0% | -1.825% | 32.76% | 29.51% | 26.96% | 27.82% | 14.88%
NTS exit costs | 21.4903 | 20.8221 | 19.8623 | 20.846 | 21.2389 | 20.2136 | 20.5279 | 18.9296 | 163.9307 |  | NTS exit costs | 0 | 0 | 0 | -0.012713 | 0.39402 | -2.3962 | 1.2122 | 1.844 | 1.0414 | NTS exit costs | 0% | 0% | 0% | -0.06099% | 1.855% | -11.85% | 5.905% | 9.742% | 0.6353%
Shrinkage | 7.2817 | 5.0932 | 3.8533 | 3.1988 | 3.1746 | 3.1513 | 3.0771 | 2.9893 | 31.8192 |  | Shrinkage | 0 | 0 | 0 | 0.48351 | 0.56952 | 0.61041 | 0.7033 | 0.80597 | 3.1727 | Shrinkage | 0% | 0% | 0% | 15.12% | 17.94% | 19.37% | 22.86% | 26.96% | 9.971%
NTS pensions contributions | 3.9222 | 3.9813 | 5.5237 | 5.4625 | 5.4625 | 5.4625 | 5.4625 | 5.4625 | 40.7395 |  | NTS pensions contributions | 0 | 0 | 0 | -0.026577 | -2.068 | -2.068 | -5.4625 | -5.4625 | -15.0876 | NTS pensions contributions | 0% | 0% | 0% | -0.4865% | -37.86% | -37.86% | -100% | -100% | -37.03%
Total non-controllable costs | 62.2671 | 62.006 | 60.9445 | 62.6837 | 63.2956 | 62.3922 | 63.3056 | 61.3883 | 498.283 |  | Total non-controllable costs | 0 | 0 | 0 | -0.16129 | 9.8451 | 6.0517 | 5.6836 | 6.6497 | 28.0688 | Total non-controllable costs | 0% | 0% | 0% | -0.2573% | 15.55% | 9.699% | 8.978% | 10.83% | 5.633%
Total funded costs - including uncertainties | 231.6062 | 219.9096 | 239.002 | 235.1956 | 232.1334 | 228.3591 | 227.8372 | 221.2591 | 1835.3022 |  | Total funded costs - including uncertainties | 0 | 0 | 0 | -0.91524 | 13.9382 | 5.0313 | 2.2518 | 2.4222 | 22.7282 | Total funded costs - including uncertainties | 0% | 0% | 0% | -0.3891% | 6.004% | 2.203% | 0.9883% | 1.095% | 1.238%
Of which: uncertainties*: | [10 empty] | Of which: uncertainties*: | [9 empty] | Of which: uncertainties*:
Smart metering | 0.096951 | 0.18291 | 0.30061 | 0.858 | 4.0235 | 5.3631 | 3.3434 | 3.1398 | 17.3083 |  | Smart metering | 0 | 0 | 0 | -0.27159 | -0.81245 | -1.083 | -0.67513 | -0.63401 | -3.4762 | Smart metering | 0 | 0 | 0 | -0.31654 | -0.20193 | -0.20193 | -0.20193 | -0.20193 | -0.20084
Streetworks | 0.89477 | 1.3454 | 1.1643 | 0 | 0 | 0 | 0 | 0 | 3.4044 |  | Streetworks | 0 | 0 | 0 | 1.6993 | 0 | 0 | 0 | 0 | 1.6993 | Streetworks | 0 | 0 | 0 | [5 empty] | 0.49913
Physical Security Upgrade Programme (PSUP) | -0.12873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.12873 |  | Physical Security Upgrade Programme (PSUP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Physical Security Upgrade Programme (PSUP) | 0 | [7 empty] | 0
Statutory independent undertakings (SIUs) | - | - | - | - | - | - | - | - | - |  | Statutory independent undertakings (SIUs) | - | - | - | - | - | - | - | - | - | Statutory independent undertakings (SIUs) | - | - | - | - | - | - | - | - | -
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other
Total uncertainties* | 0.86299 | 1.5283 | 1.4649 | 0.858 | 4.0235 | 5.3631 | 3.3434 | 3.1398 | 20.584 |  | Total uncertainties* | 0 | 0 | 0 | 1.4277 | -0.81245 | -1.083 | -0.67513 | -0.63401 | -1.7769 | Total uncertainties* | 0 | 0 | 0 | 1.664 | -0.20193 | -0.20193 | -0.20193 | -0.20193 | -0.086323
Total funded costs - excluding uncertainties* | 230.7432 | 218.3813 | 237.5372 | 234.3376 | 228.1099 | 222.996 | 224.4938 | 218.1193 | 1814.7182 |  | Total funded costs - excluding uncertainties* | 0 | 0 | 0 | -2.3429 | 14.7506 | 6.1142 | 2.9269 | 3.0562 | 24.5051 | Total funded costs - excluding uncertainties* | 0 | 0 | 0 | -0.009998 | 0.064665 | 0.027419 | 0.013038 | 0.014012 | 0.013504
Final proposals adjusted with agreed uncertainties - £m | [10 empty] | Variance from final proposals adjusted with uncertainties | [9 empty] | % Variance from final proposals adjusted with uncertainties
2016/17 prices
| Ofgem Allowance (Post IQI) £m | [10 empty] | Ofgem Allowance (Post IQI) £m | [9 empty] | Ofgem Allowance (Post IQI) £m
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
LTS, storage and entry | 4.0764 | 4.5369 | 5.1992 | 4.153 | 4.7823 | 5.8249 | 4.1846 | 3.5815 | 36.3388 |  | LTS, storage and entry | 0.36213 | 1.7551 | -2.752 | 0.88481 | 0.5282 | -0.78647 | 0.22791 | 1.3252 | 1.5449 | LTS, storage and entry | 8.884% | 38.68% | -52.93% | 21.31% | 11.04% | -13.5% | 5.446% | 37% | 4.251%
Connections | 5.7214 | 5.7792 | 5.8436 | 5.869 | 5.93 | 5.9523 | 5.9271 | 5.9276 | 46.9503 |  | Connections | -0.86146 | -0.40342 | 0.88328 | -1.0477 | -0.0062907 | -0.25366 | -0.35197 | -0.41037 | -2.4516 | Connections | -15.06% | -6.981% | 15.12% | -17.85% | -0.1061% | -4.262% | -5.938% | -6.923% | -5.222%
Mains Reinforcement | 1.2485 | 2.1639 | 2.1157 | 2.3153 | 2.782 | 2.5937 | 2.4957 | 2.5418 | 18.2567 |  | Mains Reinforcement | -0.44519 | -1.9902 | -1.7098 | -1.6633 | -1.8465 | -1.6937 | -1.5457 | -1.5418 | -12.4362 | Mains Reinforcement | -35.66% | -91.97% | -80.81% | -71.84% | -66.37% | -65.3% | -61.94% | -60.66% | -68.12%
Governors (Replacement) | 0.53186 | 0.6354 | 0.65026 | 0.6672 | 0.76223 | 0.77315 | 0.76916 | 0.79002 | 5.5793 |  | Governors (Replacement) | 0.16192 | -0.090828 | -0.078444 | -0.026645 | 0.88162 | 0.8958 | 0.89304 | 0.92044 | 3.5569 | Governors (Replacement) | 30.44% | -14.29% | -12.06% | -3.994% | 115.7% | 115.9% | 116.1% | 116.5% | 63.75%
Other Capex | 19.6527 | 19.4496 | 9.9916 | 8.82 | 12.451 | 10.5775 | 10.7525 | 6.1971 | 97.892 |  | Other Capex | -8.0126 | -7.81 | -0.77758 | 1.3612 | -3.7714 | -2.3628 | -0.96512 | 3.6624 | -18.676 | Other Capex | -40.77% | -40.16% | -7.782% | 15.43% | -30.29% | -22.34% | -8.976% | 59.1% | -19.08%
of which IT | 5.2801 | 2.9688 | 3.43 | 1.716 | 2.843 | 1.7585 | 1.665 | 0.61854 | 20.2799 |  | of which IT | 1.9001 | 2.9053 | 0.95528 | 0.88503 | -1.676 | -0.59147 | 1.3081 | 2.3545 | 8.0408 | of which IT | 35.99% | 97.86% | 27.85% | 51.58% | -58.95% | -33.63% | 78.56% | 380.7% | 39.65%
of which Vehicles | 1.7713 | 4.4423 | 1.1234 | 1.3299 | 2.9053 | 2.286 | 3.6552 | 1.1576 | 18.6711 |  | of which Vehicles | 0.010239 | -3.2839 | 0.2903 | 1.6597 | -0.034649 | -0.31715 | -2.0776 | 0.044407 | -3.7087 | of which Vehicles | 0.578% | -73.92% | 25.84% | 124.8% | -1.193% | -13.87% | -56.84% | 3.836% | -19.86%
Total Capex | 31.2308 | 32.5651 | 23.8003 | 21.8245 | 26.7076 | 25.7216 | 24.1292 | 19.038 | 205.0171 |  | Total Capex | -8.7952 | -8.5393 | -4.4345 | -0.49163 | -4.2144 | -4.2009 | -1.7419 | 3.9559 | -28.4619 | Total Capex | -28.16% | -26.22% | -18.63% | -2.253% | -15.78% | -16.33% | -7.219% | 20.78% | -13.88%
HSE driven mains & services | -1.3474 | -2.1944 | -2.0694 | 0 | 0 | 0 | 0 | 0 | -5.6111 |  | HSE driven mains & services | 59.249 | 47.1643 | 68.6899 | 57.4715 | 51.2219 | 51.4182 | 51.4182 | 51.1122 | 437.7451 | HSE driven mains & services | -4397% | -2149% | -3319% | [5 empty] | -7801%
Non-HSE driven mains & services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Non-HSE driven mains & services | 5.5566 | 8.2223 | 14.0095 | 14.5351 | 14.5109 | 10.7545 | 9.0585 | 7.6416 | 84.289 | Non-HSE driven mains & services
Multi occupancy buildings (MoBs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Multi occupancy buildings (MoBs) | 0.30586 | 1.6545 | 2.0271 | 0.65921 | 0.9733 | 0.80978 | 0.81361 | 0.83072 | 8.0741 | Multi occupancy buildings (MoBs)
Total Repex | 85.4124 | 84.7993 | 85.2406 | 86.9335 | 87.2069 | 87.4569 | 87.72 | 87.9466 | 692.7163 |  | Total Repex | -21.6483 | -29.9526 | -2.5835 | -14.2677 | -20.5008 | -24.4745 | -26.4297 | -28.3621 | -168.2191 | Total Repex | -25.35% | -35.32% | -3.031% | -16.41% | -23.51% | -27.98% | -30.13% | -32.25% | -24.28%
Work Management | 19.0013 | 18.2586 | 18.4591 | 18.0588 | 18.7273 | 19.0929 | 20.2489 | 18.8985 | 150.7455 |  | Work Management | 6.6366 | 1.7762 | 0.4511 | 0.56209 | 0.10255 | -0.94999 | -3.0803 | -2.1133 | 3.385 | Work Management | 34.93% | 9.728% | 2.444% | 3.113% | 0.5476% | -4.976% | -15.21% | -11.18% | 2.245%
Emergency | 11.7852 | 11.7324 | 11.7276 | 11.7807 | 11.801 | 11.7312 | 11.666 | 11.6015 | 93.8255 |  | Emergency | -3.0775 | -2.6384 | -3.2001 | -3.2341 | -2.1751 | -1.9081 | -1.4376 | -1.6223 | -19.2932 | Emergency | -26.11% | -22.49% | -27.29% | -27.45% | -18.43% | -16.26% | -12.32% | -13.98% | -20.56%
Repair | 10.0597 | 9.8863 | 9.6918 | 9.256 | 8.9242 | 8.5676 | 8.195 | 7.7949 | 72.3756 |  | Repair | 0.31117 | 0.49056 | -0.49729 | 1.4722 | 1.279 | 1.4095 | 1.3411 | 1.6115 | 7.4177 | Repair | 3.093% | 4.962% | -5.131% | 15.91% | 14.33% | 16.45% | 16.36% | 20.67% | 10.25%
Maintenance | 11.9553 | 12.6212 | 13.0524 | 13.1407 | 13.4759 | 13.5778 | 13.4705 | 13.3662 | 104.6601 |  | Maintenance | -3.714 | -3.251 | -2.8111 | -1.8725 | -0.16976 | -1.1224 | -0.68981 | -2.6329 | -16.2634 | Maintenance | -31.07% | -25.76% | -21.54% | -14.25% | -1.26% | -8.266% | -5.121% | -19.7% | -15.54%
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Statutory independent undertakings (SIUs) | - | - | - | - | - | - | - | - | - | Statutory independent undertakings (SIUs) | - | - | - | - | - | - | - | - | -
Other Direct Activities | 6.9731 | 6.1779 | 6.8582 | 7.3716 | 4.7908 | 4.3822 | 3.8852 | 3.3921 | 43.831 |  | Other Direct Activities | -1.0507 | 0.022055 | -0.74533 | -2.0425 | 0.43169 | 0.2007 | 0.69583 | 1.1846 | -1.3037 | Other Direct Activities | -15.07% | 0.357% | -10.87% | -27.71% | 9.011% | 4.58% | 17.91% | 34.92% | -2.974%
of which Xoserve | 4.296 | 4.1779 | 4.816 | 5.2732 | 2.6757 | 2.2469 | 1.7596 | 1.2924 | 26.5377 |  | of which Xoserve | -0.93697 | -0.45527 | -1.3724 | -2.2933 | -0.028087 | -0.15357 | 0.33365 | 0.80091 | -4.1051 | of which Xoserve | -21.81% | -10.9% | -28.5% | -43.49% | -1.05% | -6.835% | 18.96% | 61.97% | -15.47%
Total Direct Opex | 59.7747 | 58.6763 | 59.7891 | 59.6079 | 57.7192 | 57.3517 | 57.4656 | 55.0532 | 465.4376 |  | Total Direct Opex | -0.89447 | -3.6006 | -6.8027 | -5.1147 | -0.53158 | -2.3702 | -3.1709 | -3.5724 | -26.0576 | Total Direct Opex | -1.496% | -6.136% | -11.38% | -8.581% | -0.921% | -4.133% | -5.518% | -6.489% | -5.599%
Business support | 16.8205 | 17.0093 | 17.0694 | 17.028 | 17.0887 | 17.3366 | 17.485 | 17.6126 | 137.4501 |  | Business support | 5.9494 | 5.7248 | 4.1942 | 3.4726 | 5.6834 | 4.6459 | 2.4779 | 1.0548 | 33.2029 | Business support | 35.37% | 33.66% | 24.57% | 20.39% | 33.26% | 26.8% | 14.17% | 5.989% | 24.16%
Training & Apprentices | 1.5574 | 1.7224 | 1.9973 | 2.2781 | 2.5569 | 2.4186 | 2.2975 | 2.326 | 17.1543 |  | Training & Apprentices | -0.068051 | -0.50103 | -0.21276 | 0.48749 | 1.215 | 1.0608 | 0.8668 | 0.59078 | 3.4391 | Training & Apprentices | -4.369% | -29.09% | -10.65% | 21.4% | 47.52% | 43.86% | 37.73% | 25.4% | 20.05%
Total Indirect Opex | 18.3779 | 18.7317 | 19.0668 | 19.306 | 19.6457 | 19.7552 | 19.7826 | 19.9386 | 154.6044 |  | Total Indirect Opex | 5.8813 | 5.2238 | 3.9814 | 3.96 | 6.8984 | 5.7067 | 3.3447 | 1.6456 | 36.6419 | Total Indirect Opex | 32% | 27.89% | 20.88% | 20.51% | 35.11% | 28.89% | 16.91% | 8.253% | 23.7%
Total Opex | 78.923 | 78.1784 | 79.6263 | 79.6843 | 78.1353 | 77.8773 | 78.0187 | 75.7622 | 626.2056 |  | Total Opex | 4.2164 | 0.85273 | -3.5917 | -1.9251 | 5.5964 | 2.566 | -0.59662 | -2.6973 | 4.4207 | Total Opex | 5.342% | 1.091% | -4.511% | -2.416% | 7.162% | 3.295% | -0.7647% | -3.56% | 0.706%
Total sub-deducts | 1.5409 | 1.5409 | 1.5409 | 1.5409 | 1.5409 | 1.5409 | 1.5409 | 1.5409 | 12.3273 |  | Total sub-deducts | -1.2646 | -1.5405 | -1.4608 | -1.4136 | -1.5409 | -1.5409 | -1.5409 | -1.5409 | -12.3273 | Total sub-deducts | -82.07% | -99.97% | -94.8% | -91.74% | -100% | -100% | -100% | -100% | -100%
Total Controllable costs | 195.5662 | 195.5428 | 188.6673 | 188.4424 | 192.0498 | 191.0559 | 189.8679 | 182.7468 | 1523.939 |  | Total Controllable costs | -26.2271 | -37.6392 | -10.6097 | -16.6845 | -19.1188 | -26.1094 | -28.7682 | -27.1034 | -192.2603 | Total Controllable costs | -13.41% | -19.25% | -5.624% | -8.854% | -9.955% | -13.67% | -15.15% | -14.83% | -12.62%
Non-Controllable costs | [10 empty] | Non-Controllable costs | [9 empty] | Non-Controllable costs
Licence/network/other | 27.0471 | 27.0944 | 27.1028 | 27.1028 | 27.1028 | 27.1028 | 27.1028 | 27.1028 | 216.7583 |  | Licence/network/other | 2.5258 | 5.015 | 4.6024 | 5.4681 | 17.2665 | 16.3675 | 16.366 | 16.3662 | 83.9775 | Licence/network/other | 9.338% | 18.51% | 16.98% | 20.18% | 63.71% | 60.39% | 60.38% | 60.39% | 38.74%
NTS exit costs | 21.4027 | 21.0749 | 20.7115 | 20.7115 | 20.7115 | 20.7115 | 20.7115 | 20.7115 | 166.7466 |  | NTS exit costs | 0.087535 | -0.25281 | -0.84918 | 0.12184 | 0.9214 | -2.894 | 1.0286 | 0.06219 | -1.7745 | NTS exit costs | 0.409% | -1.2% | -4.1% | 0.5883% | 4.449% | -13.97% | 4.966% | 0.3003% | -1.064%
Shrinkage | 8.6717 | 8.5645 | 8.5068 | 8.3475 | 8.2252 | 8.1026 | 7.9737 | 7.8243 | 66.2163 |  | Shrinkage | -1.39 | -3.4713 | -4.6535 | -4.6652 | -4.4811 | -4.3409 | -4.1933 | -4.029 | -31.2244 | Shrinkage | -16.03% | -40.53% | -54.7% | -55.89% | -54.48% | -53.57% | -52.59% | -51.49% | -47.16%
NTS pensions contributions | 3.9405 | 3.9405 | 3.9405 | 3.9405 | 3.9405 | 3.9405 | 3.9405 | 3.9405 | 31.5242 |  | NTS pensions contributions | -0.018275 | 0.040791 | 1.5832 | 1.4954 | -0.54611 | -0.54611 | -3.9405 | -3.9405 | -5.8722 | NTS pensions contributions | -0.4638% | 1.035% | 40.18% | 37.95% | -13.86% | -13.86% | -100% | -100% | -18.63%
Total non-controllable costs | 61.062 | 60.6743 | 60.2616 | 60.1023 | 59.98 | 59.8575 | 59.7285 | 59.5791 | 481.2454 |  | Total non-controllable costs | 1.205 | 1.3317 | 0.68287 | 2.4201 | 13.1607 | 8.5864 | 9.2607 | 8.4589 | 45.1064 | Total non-controllable costs | 1.973% | 2.195% | 1.133% | 4.027% | 21.94% | 14.34% | 15.5% | 14.2% | 9.373%
Total funded costs - including agreed uncertainties** | 256.6282 | 256.2171 | 248.9289 | 248.5447 | 252.0297 | 250.9133 | 249.5965 | 242.3259 | 2005.1844 |  | Total funded costs - including uncertainties | -25.0221 | -36.3075 | -9.9268 | -14.2644 | -5.9581 | -17.5229 | -19.5075 | -18.6445 | -147.1539 | Total funded costs - including uncertainties | -9.75% | -14.17% | -3.988% | -5.739% | -2.364% | -6.984% | -7.816% | -7.694% | -7.339%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | -0.74467
Final proposals - £m
2009/10 prices
Ofgem Allowance (Post IQI) £m
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
LTS, storage and entry | 3.3191 | 3.6941 | 4.2334 | 3.3815 | 3.8939 | 4.7429 | 3.4073 | 2.9162 | 29.5885
Connections | 4.6586 | 4.7057 | 4.7581 | 4.7787 | 4.8284 | 4.8466 | 4.8261 | 4.8265 | 38.2287
Mains Reinforcement | 1.0166 | 1.7619 | 1.7227 | 1.8852 | 2.2652 | 2.1119 | 2.0321 | 2.0696 | 14.8653
Governors (Replacement) | 0.43306 | 0.51737 | 0.52947 | 0.54326 | 0.62064 | 0.62953 | 0.62628 | 0.64326 | 4.5429
Other Capex | 16.002 | 15.835 | 8.1205 | 7.1663 | 10.3616 | 8.9333 | 9.1713 | 5.5086 | 81.0985
of which IT | 4.2993 | 2.4158 | 2.7778 | 1.3819 | 2.5384 | 1.7526 | 1.7718 | 0.9663 | 17.9038
of which Vehicles | 1.4423 | 3.6171 | 0.91469 | 1.0829 | 2.3656 | 1.8614 | 2.9762 | 0.94258 | 15.2027
Total Capex | 25.4293 | 26.5142 | 19.3641 | 17.7551 | 21.9698 | 21.2643 | 20.0631 | 15.9641 | 168.3239
HSE driven mains & services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-HSE driven mains & services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Multi occupancy buildings (MoBs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Repex | 70.6431 | 70.8336 | 71.0912 | 70.7846 | 71.0072 | 71.2108 | 71.425 | 71.6095 | 568.6051
Work Management | 15.4716 | 14.8669 | 15.0301 | 14.7042 | 15.2485 | 15.5462 | 16.4874 | 15.3879 | 122.7428
Emergency | 9.596 | 9.5529 | 9.5491 | 9.5923 | 9.6088 | 9.552 | 9.4989 | 9.4464 | 76.3963
Repair | 8.191 | 8.0498 | 7.8914 | 7.5366 | 7.2664 | 6.976 | 6.6727 | 6.3469 | 58.931
Maintenance | 9.7345 | 10.2766 | 10.6278 | 10.6997 | 10.9726 | 11.0556 | 10.9682 | 10.8833 | 85.2183
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Activities | 5.6777 | 5.0214 | 5.4988 | 5.9156 | 5.1672 | 5.3857 | 5.5217 | 5.3837 | 43.5719
of which Xoserve | 3.498 | 3.393 | 3.836 | 4.207 | 3.445 | 3.647 | 3.791 | 3.674 | 29.491
Total Direct Opex | 48.6708 | 47.7677 | 48.5972 | 48.4484 | 48.2635 | 48.5155 | 49.149 | 47.4482 | 386.8602
Business support | 13.6959 | 13.8496 | 13.8986 | 13.8648 | 13.9143 | 14.1161 | 14.237 | 14.3408 | 111.9172
Training & Apprentices | 1.2681 | 1.4024 | 1.6263 | 1.8549 | 2.0819 | 1.9693 | 1.8707 | 1.8939 | 13.9677
Total Indirect Opex | 14.964 | 15.2521 | 15.5249 | 15.7197 | 15.9963 | 16.0854 | 16.1077 | 16.2347 | 125.8848
Total Opex | 64.2622 | 63.647 | 64.7494 | 64.7954 | 64.8871 | 65.2283 | 65.884 | 64.3102 | 517.7637
Total sub-deducts | 1.2547 | 1.2547 | 1.2547 | 1.2547 | 1.2547 | 1.2547 | 1.2547 | 1.2547 | 10.0373
Total Controllable costs | 160.3346 | 160.9948 | 155.2047 | 153.3351 | 157.8642 | 157.7033 | 157.3722 | 151.8838 | 1254.6928
Non-Controllable costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Licence/network/other | 22.0228 | 22.0613 | 22.0682 | 22.0682 | 22.0682 | 22.0682 | 22.0682 | 22.0682 | 176.493
NTS exit costs | 17.4269 | 17.16 | 16.8641 | 16.8641 | 16.8641 | 16.8641 | 16.8641 | 16.8641 | 135.7715
Shrinkage | 7.0608 | 6.9736 | 6.9266 | 6.7969 | 6.6972 | 6.5975 | 6.4925 | 6.3708 | 53.9159
NTS pensions contributions | 3.2085 | 3.2085 | 3.2085 | 3.2085 | 3.2085 | 3.2085 | 3.2085 | 3.2085 | 25.6682
Total non-controllable costs | 49.7191 | 49.4034 | 49.0673 | 48.9376 | 48.838 | 48.7382 | 48.6333 | 48.5116 | 391.8485
Total funded costs | 210.0537 | 210.3982 | 204.272 | 202.2728 | 206.7022 | 206.4416 | 206.0055 | 200.3954 | 1646.5413
Agreed Uncertainties** £m | [8 empty] | ok
2009-10 prices
Ofgem Allowance (Post IQI) £m
Uncertainty | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
Smart metering | [8 empty] | 0
Streetworks | [8 empty] | 0
PSUP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SIUs | [8 empty] | 0
Other - fuel poor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tier 2A adjustment | -1.0971 | -1.7868 | -1.685 | [5 empty] | -4.5688
Central Agent (FGO) | -4.4188e-07 | 0.010406 | 0.10045 | 0.10192 | -1.4898 | -2.1383 | -2.7744 | -3.0844 | -9.2741
Total | -1.0971 | -1.7763 | -1.5845 | 0.10192 | -1.4898 | -2.1383 | -2.7744 | -3.0844 | -13.8429
[9 empty] | 0 | check
Agreed uncertainties** by activity £m
Ofgem Allowance (Post IQI) £m
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
LTS, storage and entry | [8 empty] | 0
Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mains Reinforcement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Governors (Replacement) | [8 empty] | 0
Other Capex | -6.6282e-08 | 0.0015609 | 0.015067 | 0.015287 | -0.22347 | -0.32074 | -0.41616 | -0.46265 | -1.3911
of which IT | -6.6282e-08 | 0.0015609 | 0.015067 | 0.015287 | -0.22347 | -0.32074 | -0.41616 | -0.46265 | -1.3911
of which Vehicles | [8 empty] | 0
Total Capex | -6.6282e-08 | 0.0015609 | 0.015067 | 0.015287 | -0.22347 | -0.32074 | -0.41616 | -0.46265 | -1.3911
HSE driven mains & services | -1.0971 | -1.7868 | -1.685 | 0 | 0 | 0 | 0 | 0 | -4.5688
Non-HSE driven mains & services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Multi occupancy buildings (MoBs) | [8 empty] | 0
Total Repex | -1.0971 | -1.7868 | -1.685 | 0 | 0 | 0 | 0 | 0 | -4.5688
Work Management | [8 empty] | 0
Emergency | [8 empty] | 0
Repair | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Statutory independent undertakings (SIUs) | [8 empty] | 0
Other Direct Activities | -3.756e-07 | 0.0088452 | 0.085381 | 0.086628 | -1.2664 | -1.8175 | -2.3582 | -2.6217 | -7.883
of which Xoserve | -3.756e-07 | 0.0088452 | 0.085381 | 0.086628 | -1.2664 | -1.8175 | -2.3582 | -2.6217 | -7.883
Total Direct Opex | -3.756e-07 | 0.0088452 | 0.085381 | 0.086628 | -1.2664 | -1.8175 | -2.3582 | -2.6217 | -7.883
Business support | [8 empty] | 0
Training & Apprentices | [8 empty] | 0
Total Indirect Opex | [8 empty] | 0
Total Opex | -3.756e-07 | 0.0088452 | 0.085381 | 0.086628 | -1.2664 | -1.8175 | -2.3582 | -2.6217 | -7.883
Total Controllable costs | -1.0971 | -1.7763 | -1.5845 | 0.10192 | -1.4898 | -2.1383 | -2.7744 | -3.0844 | -13.8429
0
| OK | OK | OK | OK | OK | OK | OK | OK | OK
* These are uncertainties where a reopener has yet to be triggered and no decision on setting an allowance has been made.
** Agreed uncertainties are where a reopener has been triggered and a decision has been made by Ofgem.

## 2.3 Workload summary
Regulatory Reporting Pack
Cadent West Midlands
2016/17
2.3 Summary of workload
Current year RRP submission 2015 - Workload
|  | Actuals |  |  | Current year actuals | Forecast |  |  |  | Forecast RIIO Total
Cost activity |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Opex
Mains condition reports | Number | 3321 | 4373 | 4245 | 4422 | 4304 | 4218 | 4134 | 4051 | 33068
Service condition reports | Number | 10316 | 9972 | 9930 | 10043 | 9968 | 9768 | 9573 | 9381 | 78951
No. of holders removed | Number | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4
Capex
Total mains reinforcement | km | 0.8168 | 0.218 | 2.8032 | 3.3359 | 3.152 | 2.9 | 3 | 3.1 | 19.3259
Total reinforcement Governors | Number | 1 | 0 | 2 | 3 | 2 | 2 | 2 | 2 | 14
Total connection services | Number | 3469 | 3219 | 3626 | 3560 | 4036 | 3903 | 3973 | 4047 | 29833
- New housing services | Number | 719 | 787 | 810 | 940 | 1016.7095 | 972.0924 | 996.6845 | 1021.9793 | 7263.4657
- Existing housing services | Number | 1549 | 1396 | 1640 | 1427 | 1877.2905 | 1794.9076 | 1840.3155 | 1887.0207 | 13411.5343
- Non- domestic services | Number | 71 | 87 | 85 | 81 | 82 | 83 | 84 | 85 | 658
- Fuel poor services | Number | 1130 | 949 | 1091 | 1112 | 1060 | 1053 | 1052 | 1053 | 8500
Governor intervention | Number | 17 | 44 | 13 | 33 | 9 | 9 | 8 | 8 | 141
Repex
T1 length decommissioned | km | 307.7813 | 196.2394 | 372.6743 | 331.9344 | 312.7 | 334.7 | 334.7 | 334.7 | 2525.4294
T2 length decommissioned | km | 4.3696 | 1.7072 | 6.415 | 7.0074 | 7.1 | 7.6 | 7.6 | 7.6 | 49.3992
T3 length decommissioned | km | 0.4466 | 0.438 | 1.4716 | 10.5461 | 6.2 | 2 | 2 | 2 | 25.1023
Steel length decommissioned | km | 9.8977 | 8.8776 | 28.5854 | 19.7371 | 21.2 | 22.5 | 22.5 | 22.5 | 155.7978
Other length decommissioned | km | 5.4808 | 5.1398 | 3.1182 | 9.5742 | 7.2 | 2.6 | 2.6 | 2.6 | 38.3131
No. of services transferred | Number | 10468 | 7405 | 13848 | 12623 | 11804 | 12301 | 12301 | 12301 | 93051
No. of services relaid | Number | 25939 | 20150 | 29934.7565 | 27013.306 | 27975 | 29151 | 29151 | 29151 | 218465.0625
Previous year RRP submission | [10 empty] | Variance from previous year | [10 empty] | % Variance from previous year
|  | Actuals 2014: Actuals; Current year actuals 2017: Previous year forecast |  |  |  | Actuals |  |  | Current year actuals | Forecast | [6 empty] | Actuals |  |  | Current year actuals | Forecast
Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Opex | [10 empty] | Opex | [10 empty] | Opex
Mains condition reports | Number | 3321 | 4373 | 4245 | 4126 | 4010 | 3898 | 3722 | 3682 | 31377 | Mains condition reports | Number | 0 | 0 | 0 | 296 | 294 | 320 | 412 | 369 | 1691 | Mains condition reports | Number | 0% | 0% | 0% | 7.174% | 7.332% | 8.209% | 11.07% | 10.02% | 5.389%
Service condition reports | Number | 10316 | 9972 | 9930 | 9629 | 9565 | 9475 | 9387 | 9300 | 77574 | Service condition reports | Number | 0 | 0 | 0 | 414 | 403 | 293 | 186 | 81 | 1377 | Service condition reports | Number | 0% | 0% | 0% | 4.3% | 4.213% | 3.092% | 1.981% | 0.871% | 1.775%
No. of holders removed | Number | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | No. of holders removed | Number | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No. of holders removed | Number | - | - | 0% | - | - | - | - | - | 0%
Capex | [10 empty] | Capex | [10 empty] | Capex
Total mains reinforcement | km | 0.8168 | 0.218 | 2.8032 | 0.91031 | 2.5143 | 2.5143 | 4.9567 | 4.9567 | 19.6903 | Total mains reinforcement | km | 0 | 0 | 0 | 2.4256 | 0.63771 | 0.38571 | -1.9567 | -1.8567 | -0.36439 | Total mains reinforcement | km | 0% | 0% | 0% | 266.5% | 25.36% | 15.34% | -39.48% | -37.46% | -1.851%
Total reinforcement Governors | Number | 1 | 0 | 2 | 1 | 2 | 2 | 2 | 2 | 12 | Total reinforcement Governors | Number | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | Total reinforcement Governors | Number | 0% | #DIV/0! | 0% | 200% | 0% | 0% | 0% | 0% | 16.67%
Total connection services | Number | 3469 | 3219 | 3626 | 3307 | 3316 | 3321 | 3327 | 3332 | 26917 | Total connection services | Number | 0 | 0 | 0 | 253 | 720 | 582 | 646 | 715 | 2916 | Total connection services | Number | 0% | 0% | 0% | 7.65% | 21.71% | 17.52% | 19.42% | 21.46% | 10.83%
- New housing services | Number | 719 | 787 | 810 | 843 | 843 | 845 | 847 | 849 | 6543 | - New housing services | Number | 0 | 0 | 0 | 97 | 173.7095 | 127.0924 | 149.6845 | 172.9793 | 720.4657 | - New housing services | Number | 0% | 0% | 0% | 11.51% | 20.61% | 15.04% | 17.67% | 20.37% | 11.01%
- Existing housing services | Number | 1549 | 1396 | 1640 | 1342 | 1350 | 1353 | 1357 | 1360 | 11347 | - Existing housing services | Number | 0 | 0 | 0 | 85 | 527.2905 | 441.9076 | 483.3155 | 527.0207 | 2064.5343 | - Existing housing services | Number | 0% | 0% | 0% | 6.334% | 39.06% | 32.66% | 35.62% | 38.75% | 18.19%
- Non- domestic services | Number | 71 | 87 | 85 | 84 | 85 | 85 | 85 | 85 | 667 | - Non- domestic services | Number | 0 | 0 | 0 | -3 | -3 | -2 | -1 | 0 | -9 | - Non- domestic services | Number | 0% | 0% | 0% | -3.571% | -3.529% | -2.353% | -1.176% | 0% | -1.349%
- Fuel poor services | Number | 1130 | 949 | 1091 | 1038 | 1038 | 1038 | 1038 | 1038 | 8360 | - Fuel poor services | Number | 0 | 0 | 0 | 74 | 22 | 15 | 14 | 15 | 140 | - Fuel poor services | Number | 0% | 0% | 0% | 7.129% | 2.119% | 1.445% | 1.349% | 1.445% | 1.675%
Governor intervention | Number | 17 | 44 | 13 | 15 | 32 | 32 | 33 | 33 | 219 | Governor intervention | Number | 0 | 0 | 0 | 18 | -23 | -23 | -25 | -25 | -78 | Governor intervention | Number | 0% | 0% | 0% | 120% | -71.88% | -71.88% | -75.76% | -75.76% | -35.62%
Repex | [10 empty] | Repex | [10 empty] | Repex
T1 length decommissioned | km | 307.7813 | 196.2394 | 372.6743 | 376.2583 | 318.5739 | 318.5739 | 318.5739 | 316.6103 | 2525.2852 | T1 length decommissioned | km | 0 | 0 | 0 | -44.3239 | -5.8739 | 16.1261 | 16.1261 | 18.0897 | 0.1442 | T1 length decommissioned | km | 0% | 0% | 0% | -11.78% | -1.844% | 5.062% | 5.062% | 5.714% | 0.00571%
T2 length decommissioned | km | 4.3696 | 1.7072 | 6.415 | 12.0539 | 6.2112 | 6.2112 | 6.2112 | 6.2112 | 49.3906 | T2 length decommissioned | km | 0 | 0 | 0 | -5.0465 | 0.8888 | 1.3888 | 1.3888 | 1.3888 | 0.0086495 | T2 length decommissioned | km | 0% | 0% | 0% | -41.87% | 14.31% | 22.36% | 22.36% | 22.36% | 0.01751%
T3 length decommissioned | km | 0.4466 | 0.438 | 1.4716 | 3.5827 | 4.8137 | 4.8137 | 4.8137 | 4.8137 | 25.1936 | T3 length decommissioned | km | 0 | 0 | 0 | 6.9634 | 1.3863 | -2.8137 | -2.8137 | -2.8137 | -0.091294 | T3 length decommissioned | km | 0% | 0% | 0% | 194.4% | 28.8% | -58.45% | -58.45% | -58.45% | -0.3624%
Steel length decommissioned | km | 9.8977 | 8.8776 | 28.5854 | 16.6109 | 22.959 | 22.959 | 22.959 | 22.959 | 155.8077 | Steel length decommissioned | km | 0 | 0 | 0 | 3.1262 | -1.759 | -0.45902 | -0.45902 | -0.45902 | -0.0098878 | Steel length decommissioned | km | 0% | 0% | 0% | 18.82% | -7.662% | -1.999% | -1.999% | -1.999% | -0.006346%
Other length decommissioned | km | 5.4808 | 5.1398 | 3.1182 | 3.6147 | 5.201 | 5.2075 | 5.1861 | 5.1907 | 38.139 | Other length decommissioned | km | 0 | 0 | 0 | 5.9595 | 1.999 | -2.6075 | -2.5861 | -2.5907 | 0.17408 | Other length decommissioned | km | 0% | 0% | 0% | 164.9% | 38.43% | -50.07% | -49.87% | -49.91% | 0.4564%
No. of services transferred | Number | 10468 | 7405 | 13848 | 13722.7486 | 11912.6184 | 11912.8349 | 11912.1231 | 11846.8901 | 93028.2151 | No. of services transferred | Number | 0 | 0 | 0 | -1099.7486 | -108.6184 | 388.1651 | 388.8769 | 454.1099 | 22.7849 | No. of services transferred | Number | 0% | 0% | 0% | -8.014% | -0.9118% | 3.258% | 3.265% | 3.833% | 0.02449%
No. of services relaid | Number | 25939 | 20150 | 29934.7565 | 32888.5672 | 28550.3264 | 28550.8451 | 28549.1393 | 28392.7989 | 222955.4334 | No. of services relaid | Number | 0 | 0 | 0 | -5875.2612 | -575.3264 | 600.1549 | 601.8607 | 758.2011 | -4490.3709 | No. of services relaid | Number | 0% | 0% | 0% | -17.86% | -2.015% | 2.102% | 2.108% | 2.67% | -2.014%
Final proposals | [10 empty] | Variance from final proposals | [10 empty] | % Variance from final proposals
[13 empty] | Actuals |  |  | Current year actuals | Forecast | [6 empty] | Actuals |  |  | Current year actuals | Forecast
Workload
Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
Opex | [10 empty] | Opex | [10 empty] | Opex
Mains condition reports | Number | 5213.2104 | 5073.4965 | 4938.1305 | 4807.0237 | 4680.091 | 4557.2506 | 4438.4239 | 4323.5356 | 38031.1622 | Mains condition reports | Number | -1892.2104 | -700.4965 | -693.1305 | -385.0237 | -376.091 | -339.2506 | -304.4239 | -272.5356 | -4963.1622 | Mains condition reports | Number | -36.3% | -13.81% | -14.04% | -8.01% | -8.036% | -7.444% | -6.859% | -6.304% | -13.05%
Service condition reports | Number | 6873.1777 | 6728.4159 | 6590.019 | 6256.9916 | 5896.9103 | 5508.6635 | 5091.1469 | 4643.2558 | 47588.5808 | Service condition reports | Number | 3442.8223 | 3243.5841 | 3339.981 | 3786.0084 | 4071.0897 | 4259.3365 | 4481.8531 | 4737.7442 | 31362.4192 | Service condition reports | Number | 50.09% | 48.21% | 50.68% | 60.51% | 69.04% | 77.32% | 88.03% | 102% | 65.9%
No. of holders removed | Number | c. 0-1 | c. 0-1 | c. 0-1 | c. 0-1 | c. 0-1 | c. 0-1 | c. 0-1 | c. 0-1 | c. 4-5 | No. of holders removed | Number | [9 empty] | No. of holders removed | Number | [8 empty] | #VALUE!
Capex | [10 empty] | Capex | [10 empty] | Capex
Total mains reinforcement | km | 3.4 | 6.9 | 5.8 | 6.7 | 8.01 | 7.59 | 7.21 | 7.09 | 52.7 | Total mains reinforcement | km | -2.5832 | -6.682 | -2.9968 | -3.3641 | -4.858 | -4.69 | -4.21 | -3.99 | -33.3741 | Total mains reinforcement | km | -75.98% | -96.84% | -51.67% | -50.21% | -60.65% | -61.79% | -58.39% | -56.28% | -63.33%
Total reinforcement Governors | Number | 3 | 2 | 3 | 2 | 4 | 3 | 3 | 4 | 24 | Total reinforcement Governors | Number | -2 | -2 | -1 | 1 | -2 | -1 | -1 | -2 | -10 | Total reinforcement Governors | Number | -66.67% | -100% | -33.33% | 50% | -50% | -33.33% | -33.33% | -50% | -41.67%
Total connection services | Number | 4044.7936 | 4087.0812 | 4156.8477 | 4199.1216 | 4232.6865 | 4230.1402 | 4230.1402 | 4220.1402 | 33400.9513 | Total connection services | Number | -575.7936 | -868.0812 | -530.8477 | -639.1216 | -196.6865 | -327.1402 | -257.1402 | -173.1402 | -3567.9513 | Total connection services | Number | -14.24% | -21.24% | -12.77% | -15.22% | -4.647% | -7.734% | -6.079% | -4.103% | -10.68%
- New housing services | Number | 704.7936 | 747.0812 | 806.8477 | 839.1216 | 872.6865 | 890.1402 | 890.1402 | 890.1402 | 6640.9513 | - New housing services | Number | 14.2064 | 39.9188 | 3.1523 | 100.8784 | 144.0231 | 81.9521 | 106.5443 | 131.8391 | 622.5144 | - New housing services | Number | 2.016% | 5.343% | 0.3907% | 12.02% | 16.5% | 9.207% | 11.97% | 14.81% | 9.374%
- Existing housing services | Number | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 18400 | - Existing housing services | Number | -751 | -904 | -660 | -873 | -422.7095 | -505.0924 | -459.6845 | -412.9793 | -4988.4657 | - Existing housing services | Number | -32.65% | -39.3% | -28.7% | -37.96% | -18.38% | -21.96% | -19.99% | -17.96% | -27.11%
- Non- domestic services | Number | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - Non- domestic services | Number | 71 | 87 | 85 | 81 | 82 | 83 | 84 | 85 | 658 | - Non- domestic services | Number
- Fuel poor services | Number | 1040 | 1040 | 1050 | 1060 | 1060 | 1040 | 1040 | 1030 | 8360 | - Fuel poor services | Number | 90 | -91 | 41 | 52 | 0 | 13 | 12 | 23 | 140 | - Fuel poor services | Number | 8.654% | -8.75% | 3.905% | 4.906% | 0% | 1.25% | 1.154% | 2.233% | 1.675%
Governor intervention | Number | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 59 | Governor intervention | Number | 11 | 37 | 6 | 26 | 1 | 1 | 0 | 0 | 82 | Governor intervention | Number | 183.3% | 528.6% | 85.71% | 371.4% | 12.5% | 12.5% | 0% | 0% | 139%
Repex | [10 empty] | Repex | [10 empty] | Repex
T1 length decommissioned | km | 324.0104 | 323.3831 | 322.778 | 322.0627 | 321.4997 | 320.9568 | 320.4332 | 319.9285 | 2575.0523 | T1 length decommissioned | km | -16.2291 | -127.1437 | 49.8963 | 9.8717 | -8.7997 | 13.7432 | 14.2668 | 14.7715 | -49.6229 | T1 length decommissioned | km | -5.009% | -39.32% | 15.46% | 3.065% | -2.737% | 4.282% | 4.452% | 4.617% | -1.927%
T2 length decommissioned | km | 9.0431 | 9.0432 | 9.0433 | 9.0417 | 9.0418 | 9.0418 | 9.0419 | 9.042 | 72.3389 | T2 length decommissioned | km | -4.6735 | -7.336 | -2.6283 | -2.0343 | -1.9418 | -1.4418 | -1.4419 | -1.442 | -22.9397 | T2 length decommissioned | km | -51.68% | -81.12% | -29.06% | -22.5% | -21.48% | -15.95% | -15.95% | -15.95% | -31.71%
T3 length decommissioned | km | 3.3471 | 3.3471 | 3.3472 | 3.346 | 3.3461 | 3.3461 | 3.3462 | 3.3462 | 26.7721 | T3 length decommissioned | km | -2.9005 | -2.9091 | -1.8756 | 7.2001 | 2.8539 | -1.3461 | -1.3462 | -1.3462 | -1.6698 | T3 length decommissioned | km | -86.66% | -86.91% | -56.03% | 215.2% | 85.29% | -40.23% | -40.23% | -40.23% | -6.237%
Steel length decommissioned | km | 16.1602 | 16.1439 | 16.1282 | 15.416 | 15.4013 | 15.3872 | 15.3736 | 15.3604 | 125.3708 | Steel length decommissioned | km | -6.2625 | -7.2663 | 12.4572 | 4.3211 | 5.7987 | 7.1128 | 7.1264 | 7.1396 | 30.427 | Steel length decommissioned | km | -38.75% | -45.01% | 77.24% | 28.03% | 37.65% | 46.23% | 46.36% | 46.48% | 24.27%
Other length decommissioned | km | 6.5873 | 6.5874 | 6.5876 | 6.5851 | 6.5853 | 6.5854 | 6.5855 | 6.5856 | 52.6891 | Other length decommissioned | km | -1.1064 | -1.4476 | -3.4694 | 2.9891 | 0.61475 | -3.9854 | -3.9855 | -3.9856 | -14.3761 | Other length decommissioned | km | -16.8% | -21.98% | -52.67% | 45.39% | 9.335% | -60.52% | -60.52% | -60.52% | -27.28%
No. of services transferred | Number | 11856.0608 | 11833.5693 | 11811.8701 | 11775.3888 | 11755.2283 | 11735.7861 | 11717.0392 | 11698.9649 | 94183.9076 | No. of services transferred | Number | -1388.0608 | -4428.5693 | 2036.1299 | 847.6112 | 48.7717 | 565.2139 | 583.9608 | 602.0351 | -1132.9076 | No. of services transferred | Number | -11.71% | -37.42% | 17.24% | 7.198% | 0.4149% | 4.816% | 4.984% | 5.146% | -1.203%
No. of services relaid | Number | 22127.836 | 21914.3997 | 21685.5577 | 21418.8018 | 21157.6865 | 20878.601 | 20580.2766 | 20263.0617 | 170026.2209 | No. of services relaid | Number | 3811.164 | -1764.3997 | 8249.1988 | 5594.5042 | 6817.3135 | 8272.399 | 8570.7234 | 8887.9383 | 48438.8416 | No. of services relaid | Number | 17.22% | -8.051% | 38.04% | 26.12% | 32.22% | 39.62% | 41.65% | 43.86% | 28.49%

## 2.4 Safety
Regulatory Reporting Pack
Cadent West Midlands
2016/17
2.4 Summary of safety outputs and secondary deliverables
Actual/forecast iron mains risk reduction (incidents/year x 10-6) - Primary output
| Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Mains risk b/f | 286251 | 265522 | 247618 | 222760.6689 | 204590.3091 | 188166.3091 | 175311.2861 | 162456.263
Mains risk reduction | 20729 | 17904 | 24857.3311 | 18170.3598 | 16424 | 12855.023 | 12855.023 | 12855.023
Main risk c/f | 265522 | 247618 | 222760.6689 | 204590.3091 | 188166.3091 | 175311.2861 | 162456.263 | 149601.24
Cumulative mains risk reduction | 20729 | 38633 | 63490.3311 | 81660.6909 | 98084.6909 | 110939.7139 | 123794.737 | 136649.76
Previous year forecast iron mains risk reduction (incidents/year x 10-6) | [8 empty] | Variance from previous year | [8 empty] | % Variance from previous year
| Actuals |  |  | Forecast | [5 empty] | Actuals | Forecast | [7 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Mains risk b/f | 286251 | 265522 | 247618 | 222760.6689 | 198457.0689 | 186243.1117 | 174029.1545 | 161815.1972
Mains risk reduction | 20729 | 17904 | 24857.3311 | 24303.6 | 12213.9572 | 12213.9572 | 12213.9572 | 12213.9572 | Mains risk reduction | 0 | 0 | 0 | -6133.2402 | 4210.0428 | 641.0658 | 641.0658 | 641.0658 | Mains risk reduction | 0% | 0% | 0% | -25.24% | 34.47% | 5.249% | 5.249% | 5.249%
Main risk c/f | 265522 | 247618 | 222760.6689 | 198457.0689 | 186243.1117 | 174029.1545 | 161815.1972 | 149601.24
Cumulative mains risk reduction | 20729 | 38633 | 63490.3311 | 87793.9311 | 100007.8883 | 112221.8456 | 124435.8028 | 136649.76 | Cumulative mains risk reduction | 0 | 0 | 0 | -6133.2402 | -1923.1974 | -1282.1316 | -641.0658 | 0 | Cumulative mains risk reduction | 0% | 0% | 0% | -6.986% | -1.923% | -1.142% | -0.5152% | 0%
Final proposals allowed iron mains risk reduction for RIIO-GD1 (incidents/year x 10-6) | [8 empty] | Variance from final proposals | [8 empty] | % Variance from final proposals
| Final proposals | [8 empty] | Final proposals | [8 empty] | Final proposals
Mains risk reduction | 131394 | [7 empty] | Mains risk reduction | 5255.76 | [7 empty] | Mains risk reduction | -100%
Actual/forecast repair risk (x106)
| Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Repair risk 2013 (start position) | 2502277
Annual repair risk | 3037830 | 3327379 | 2310117 | 2114524 | 2377163 | 2377163 | 2377163 | 2377163
Movement in risk | -535553 | -825102 | 192160 | 387753 | 125114 | 125114 | 125114 | 125114
Previous year's forecast repair risK (x106) | [8 empty] | Variance from previous year (x106) | [8 empty] | % Variance from previous year
| Actuals |  |  | Forecast | [5 empty] | Actuals |  |  | Current year actuals | Forecast |  |  |  |  | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Annual repair risk | 3037830 | 3327379 | 2310117 | 2377163 | 2377163 | 2377163 | 2377163 | 2377163 | Annual repair risk | 0 | 0 | 0 | -262639 | 0 | 0 | 0 | 0 | Repair risk reduction | 0% | 0% | 0% | -11.05% | 0% | 0% | 0% | 0%
Movement in risk | -535553 | -825102 | 192160 | 125114 | 125114 | 125114 | 125114 | 125114 | Movement in risk | 0 | 0 | 0 | 262639 | 0 | 0 | 0 | 0
Safety - Emergency response - Primary output | Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Total PREs | 83581 | 78143 | 76065 | 77899
(1) Controllable
Number of controlled gas escapes or controlled other gas emergencies reported | 28059 | 24865 | 24124 | 24483
Number of responses within timescale (2 hours) | 27732 | 24439 | 23906 | 24264
Percentage of controlled gas escapes responded to within timescale (2 hours) | 98.83% | 98.29% | 99.1% | 99.11%
(2) Non-controllable
Number of uncontrolled gas escapes or uncontrolled other gas emergencies reported | 48244 | 45430 | 43278 | 44457
Number of responses within timescale (1 hour) | 47234 | 44302 | 42687 | 43769
Percentage of uncontrolled gas escapes responded to within timescale (1 hour) | 97.91% | 97.52% | 98.63% | 98.45%
Proportion of gas escapes prevented within 12 hrs (secondary deliverable) | 43% | 50% | 51.15% | 49.47%
Gas in Buildings (GIB) events - Iron mains - Secondary deliverable | Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
GIB events reportable under RIDDOR ie GIB >= 20% LEL or > 10kg from spun/cast iron fracture or DI corrosion of mains of: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GIB events (any % level) from spun/cast iron fracture or DI corrosion of mains of: | 47 | 77 | 53 | 76
Cast/spun iron fractures and ductile iron corrosion failures - Secondary deliverable | Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Number of spun/cast iron fracture or DI corrosion of mains of: | 561 | 703 | 614 | 666 | 911 | 884 | 858 | 832
Sub-deduct networks - secondary deliverable | Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
% off sub-deduct networks taken of risk | 41.59% | 12.27% | 9% | 8% | 13% | 8% | 8% | 0%
Cumulative | 41.59% | 53.86% | 62.86% | 70.86% | 83.86% | 91.86% | 99.86% | 99.86%
Note on A71: Ofgem: Any concentration level at any location in the building. Data to include all GIB instances including those reportable under RIDDOR

## 2.5 Reliability
Regulatory Reporting Pack
Cadent West Midlands
2016/17
2.5 Summary of reliability outputs and secondary deliverables
Summary of loss of supply volumes and duration - primary output
Actual/forecast loss of supply volumes (no.)
| Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
No. of planned interruptions | 44286 | 30781 | 61702 | 50812 | 49460 | 46929 | 46929 | 46929 | 377828
No. of unplanned interruptions | 9839 | 7368 | 8338 | 6388 | 7361 | 7214 | 7070 | 6928 | 60506
Total interruptions | 54125 | 38149 | 70040 | 57200 | 56821 | 54143 | 53999 | 53857 | 438334
Previous year forecast loss of supply volumes (no.) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals |  |  | Previous year forecast | [6 empty] | Actuals |  |  | Current year actuals | Forecast | [5 empty] | Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
No. of planned interruptions | 44286 | 30781 | 61702 | 55688.7355 | 47207.7498 | 45947.9187 | 45947.9187 | 45694.5449 | 377255.8677 | No. of planned interruptions | 0 | 0 | 0 | -4876.7355 | 2252.2502 | 981.0813 | 981.0813 | 1234.4551 | 572.1323 | No. of planned interruptions | 0% | 0% | 0% | -8.757% | 4.771% | 2.135% | 2.135% | 2.702% | 0.1517%
No. of unplanned interruptions | 9839 | 7368 | 8338 | 7898 | 7675 | 7410 | 7186 | 6948 | 62662 | No. of unplanned interruptions | 0 | 0 | 0 | -1510 | -314 | -196 | -116 | -20 | -2156 | No. of unplanned interruptions | 0% | 0% | 0% | -19.12% | -4.091% | -2.645% | -1.614% | -0.2879% | -3.441%
Total interruptions | 54125 | 38149 | 70040 | 63586.7355 | 54882.7498 | 53357.9187 | 53133.9187 | 52642.5449 | 439917.8677 | Total interruptions | 0 | 0 | 0 | -6386.7355 | 1938.2502 | 785.0813 | 865.0813 | 1214.4551 | -1583.8677 | Total interruptions | 0% | 0% | 0% | -10.04% | 3.532% | 1.471% | 1.628% | 2.307% | -0.36%
Final proposals allowed loss of supply volumes (no.) | [9 empty] | Variance from final proposals | [9 empty] | Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
No. of planned interruptions | 401054.272 | [8 empty] | No. of planned interruptions | -23226.272 | [8 empty] | No. of planned interruptions | -5.791%
No. of unplanned interruptions | 70574.5548 | [8 empty] | No. of unplanned interruptions | -10068.5548 | [8 empty] | No. of unplanned interruptions | -14.27%
Total interruptions | 471628.8267 | [8 empty] | Total interruptions | -33294.8267 | [8 empty] | Total interruptions | -7.06%
Actual/forecast loss of supply duration (mins - million of)
| Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Dur. of planned interruptions | 18.5205 | 14.4199 | 22.228 | 19.126 | 20.5 | 19.4 | 19.4 | 19.4 | 152.9944
Dur. of unplanned interruptions | 8.5 | 8.4448 | 5.2156 | 4.6906 | 5.4 | 5.2 | 5 | 4.8 | 47.251
Total interruptions | 27.0205 | 22.8648 | 27.4437 | 23.8165 | 25.9 | 24.6 | 24.4 | 24.2 | 200.2454
Previous year forecast loss of supply duration (mins - million of) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals |  |  | Previous year forecast | [6 empty] | Actuals |  |  | Current year actuals | Forecast | [5 empty] | Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Dur. of planned interruptions | 18.5205 | 14.4199 | 22.228 | 23.0578 | 19.5247 | 18.9999 | 18.9999 | 18.8943 | 154.6451 | No. of planned interruptions | 0 | 0 | 0 | -3.9318 | 0.97528 | 0.40011 | 0.40011 | 0.50567 | -1.6507 | No. of planned interruptions | 0% | 0% | 0% | -17.05% | 4.995% | 2.106% | 2.106% | 2.676% | -1.067%
Dur. of unplanned interruptions | 8.5 | 8.4448 | 5.2156 | 5.5 | 5.3 | 5 | 4.8 | 4.5 | 47.2604 | No. of unplanned interruptions | 0 | 0 | 0 | -0.80941 | 0.1 | 0.2 | 0.2 | 0.3 | -0.0094107 | No. of unplanned interruptions | 0% | 0% | 0% | -14.72% | 1.887% | 4% | 4.167% | 6.667% | -0.01991%
Total interruptions | 27.0205 | 22.8648 | 27.4437 | 28.5578 | 24.8247 | 23.9999 | 23.7999 | 23.3943 | 201.9055 | Total interruptions | 0 | 0 | 0 | -4.7413 | 1.0753 | 0.60011 | 0.60011 | 0.80567 | -1.6601 | Total interruptions | 0% | 0% | 0% | -16.6% | 4.331% | 2.5% | 2.521% | 3.444% | -0.8222%
Final proposals allowed loss of supply duration (mins - million of) | [9 empty] | Variance from final proposals | [9 empty] | Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
Dur. of planned interruptions | 199.8195 | [8 empty] | No. of planned interruptions | -46.8251 | [8 empty] | No. of planned interruptions | -23.43%
Dur. of unplanned interruptions | 47.8627 | [8 empty] | No. of unplanned interruptions | -0.61165 | [8 empty] | No. of unplanned interruptions | -1.278%
Total interruptions | 247.6822 | [8 empty] | Total interruptions | -47.4367 | [8 empty] | Total interruptions | -19.15%
Summary of telemetered faults - secondary deliverables
Actual/forecast telemetered faults (fault * duration/no. of telemetered AGIs - "now faults" (hrs))
| Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Telemetered faults | 173 | 175.2 | 30.04 | 13 | 29 | 28 | 28 | 27 | 503.24
Previous year forecast telemetered faults (fault * duration/no. of telemetered AGIs - "now faults" (hrs)) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals |  |  | Previous year forecast | [6 empty] | Actuals |  | Current year actuals | Forecast | [6 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Telemetered faults | 173 | 175.2 | 30.04 | 29.4392 | 28.8504 | 28.2734 | 27.7079 | 27.1538 | 519.6647 | Telemetered faults | 0 | 0 | 0 | -16.4392 | 0.14958 | -0.27341 | 0.29206 | -0.15378 | -16.4247 | Telemetered faults | 0% | 0% | 0% | -55.84% | 0.5185% | -0.967% | 1.054% | -0.5663% | -3.161%
Final proposals allowed telemetered faults (fault * duration/no. of telemetered AGIs - "now faults" (hrs)) | [9 empty] | Variance from final proposals | [9 empty] | % Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
Telemetered faults | 127 | 123 | 119 | 116 | 112 | 108 | 105 | 101 | 911 | Telemetered faults | 46 | 52.2 | -88.96 | -103 | -83 | -80 | -77 | -74 | -407.76 | Telemetered faults | 36.22% | 42.44% | -74.76% | -88.79% | -74.11% | -74.07% | -73.33% | -73.27% | -44.76%
Summary of pressure systems safety regulations (PSSR) faults - secondary deliverables
Actual/forecast PSSR faults (faults as a % of inspections - PSSR A1 and A2 faults or faults/No. of AGIs - PSSR A1 and A2 faults (delete as appropriate))
| Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
PSSR faults (% or No.) | 5% | 5.424% | 4.724% | 13.13% | 10.69% | 6.627% | 5.813% | 5%
Previous year forecast PSSR faults (faults as a % of inspections - PSSR A1 and A2 faults or faults/No. of AGIs - PSSR A1 and A2 faults (delete as appropriate)) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals |  |  | Previous year forecast | [6 empty] | Actuals |  |  | Current year actuals | Forecast | [5 empty] | Actuals |  |  | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
PSSR faults (% or No.) | 5% | 5.424% | 4.724% | 4.19% | 4.361% | 4.328% | 4.366% | 4.234% |  | PSSR faults (% or No.) | 0 | 0 | 0 | 0.089448 | 0.063334 | 0.022986 | 0.014479 | 0.0076642 |  | PSSR faults (% or No.) | 0% | 0% | 0% | 213.5% | 145.2% | 53.1% | 33.17% | 18.1%
Final proposals allowed PSSR faults (faults as a % of inspections - PSSR A1 and A2 faults or faults/No. of AGIs - PSSR A1 and A2 faults (delete as appropriate)) | [9 empty] | Variance from final proposals | [9 empty] | % Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
PSSR faults (% or No.) | 6% | 6% | 6% | 5% | 5% | 5% | 5% | 5% | 43% | PSSR faults (% or No.) | -0.01 | -0.0057627 | -0.012765 | 0.081347 | 0.056943 | 0.016269 | 0.0081347 | 0 |  | PSSR faults (% or No.) | -16.67% | -9.605% | -21.27% | 162.7% | 113.9% | 32.54% | 16.27% | 0%
Number and value of offtake meter error reports
| Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Volume of offtake meter errors (GWh) | - | - | 0 | 0 | 0 | 0 | 0 | 0
Throughput (GWh) | 317 | 43852.7 | 42974 | 44521.1436 | 42952.8589 | 42295.9076 | 41897.8137 | 41354.1348
Meter errors/throughput (%) |  |  | 0% | 0% | 0% | 0% | 0% | 0%
Summary Capacity Utilisation
Capacity utilisation | Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
</= 50% | 42 | 43 | 50 | 50 | 50 | 51 | 51 | 51
>50% to </=70% | 34 | 34 | 35 | 37 | 37 | 36 | 36 | 36
>70% to </=80% | 19 | 19 | 14 | 14 | 14 | 14 | 14 | 14
>80% to </=100% | 21 | 21 | 17 | 16 | 16 | 16 | 16 | 16
>100% | 8 | 7 | 8 | 7 | 7 | 7 | 7 | 7
Total no. of sites | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124

## 2.6 Environmental
Regulatory Reporting Pack
Cadent West Midlands
2016/17
2.6 Summary of environmental outputs - shrinkage and leakage volumes
Actual/forecast shrinkage volumes (GWh)
| Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Shrinkage volumes at start of RIIO-GD1 | 328
Shrinkage volume | 312.5 | 302.7866 | 289.8191 | 287.3504 | 285.1621 | 275.9704 | 266.9626 | 257.9653
Shrinkage baselines | 331.3 | 323 | 316 | 310 | 302 | 295 | 289 | 281
Shrinkage volume reduction | 15.5 | 25.2134 | 38.1809 | 40.6496 | 42.8379 | 52.0296 | 61.0374 | 70.0347
% shrinkage volume reduction | 4.726% | 7.687% | 11.64% | 12.39% | 13.06% | 15.86% | 18.61% | 21.35%
Previous year forecast shrinkage volumes (GWh) | [8 empty] | Variance from previous year | [8 empty] | % Variance from previous year
| Actuals |  |  | Previous year forecast | [5 empty] | Actuals |  |  | Current year actuals | Forecast |  |  |  |  | Actuals |  |  | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Shrinkage volumes at start of RIIO-GD1 | 328
Shrinkage volume | 312.5 | 302.7866 | 289.8191 | 284 | 277 | 271 | 265 | 258 | Shrinkage volume | 0 | 0 | 0 | 3.3504 | 8.1621 | 4.9704 | 1.9626 | -0.034655 | Shrinkage volume | 0% | 0% | 0% | 1.18% | 2.947% | 1.834% | 0.7406% | -0.01343%
Shrinkage volume reduction | 15.5 | 25.2134 | 38.1809 | 44 | 51 | 57 | 63 | 70 | Shrinkage volume reduction | 0 | 0 | 0 | -3.3504 | -8.1621 | -4.9704 | -1.9626 | 0.034655 | Shrinkage volume reduction | 0% | 0% | 0% | -7.615% | -16% | -8.72% | -3.115% | 0.04951%
% shrinkage volume reduction | 4.726% | 7.687% | 11.64% | 13.41% | 15.55% | 17.38% | 19.21% | 21.34%
Final proposals allowed shrinkage volumes (GWh) | [8 empty] | Variance from final proposals | [8 empty] | % Variance from final proposals
| Final proposals | [8 empty] | Final proposals | [8 empty] | Final proposals
Shrinkage volume reduction | 15.5% | [7 empty] | Shrinkage volume reduction | 19.1947 | [7 empty] | Shrinkage volume reduction | 5.852%
Actual/forecast leakage volumes (GWh)
| Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Leakage volumes at start of RIIO-GD1 | 311.7
Leakage volume | 299.2059 | 289.016 | 276.2764 | 273.3227 | 271.0134 | 261.8864 | 252.8875 | 244.0501
Leakage baselines | 316.3 | 309 | 303 | 296 | 289 | 282 | 276 | 268
Leakage volume reduction | 12.4941 | 22.684 | 35.4236 | 38.3773 | 40.6866 | 49.8136 | 58.8125 | 67.6499
% Leakage volume reduction | 3.809% | 7.278% | 11.36% | 12.31% | 13.05% | 15.98% | 18.87% | 21.7%
Previous year forecast leakage volumes (GWh) | [8 empty] | Variance from previous year | [8 empty] | % Variance from previous year
| Actuals |  |  | Previous year forecast | [5 empty] | Actuals |  |  | Current year actuals | Forecast |  |  |  |  | Actuals |  |  | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Leakage volumes at start of RIIO-GD1 | 311.7
Leakage volume | 299.2059 | 289.016 | 276.2764 | 270 | 264 | 257 | 251 | 245 | Leakage volume | 0 | 0 | 0 | 3.3227 | 7.0134 | 4.8864 | 1.8875 | -0.94987 | Leakage volume | 0% | 0% | 0% | 1.231% | 2.657% | 1.901% | 0.752% | -0.3877%
Leakage volume reduction | 12.4941 | 22.684 | 35.4236 | 41.7 | 47.7 | 54.7 | 60.7 | 66.7 | Leakage volume reduction | 0 | 0 | 0 | -3.3227 | -7.0134 | -4.8864 | -1.8875 | 0.94987 | Leakage volume reduction | 0% | 0% | 0% | -7.968% | -14.7% | -8.933% | -3.109% | 1.424%
% Leakage volume reduction | 3.809% | 7.278% | 11.36% | 13.38% | 15.3% | 17.55% | 19.47% | 21.4%
Final proposals allowed leakage volumes (GWh) | [8 empty] | Variance from final proposals | [8 empty] | % Variance from final proposals
| Final proposals | [8 empty] | Final proposals | [8 empty] | Final proposals
Leakage volume reduction | 15.8% | [7 empty] | Leakage volume reduction | 18.4013 | [7 empty] | Leakage volume reduction | 5.904%
Note on B23: revised baseline based on lastest shrinkage/leakage model - informed as part of the SQ process
Note on B49: revised baseline based on lastest shrinkage/leakage model - informed as part of the SQ process

## 2.7 Performance Snapshot
Regulatory Reporting Pack
Cadent West Midlands
2016/17
2.7 Performance Snapshot
Network |  |  | Actual 2016/17
Number of customers directly connected to network | No. | Comparator | 1936454.5
Total GDN network length all pressure tiers | km | Comparator | 24188.1848
Network reliability
Overall network reliability | % of full delivery 24/7/365 | Comparator | 100%
Unplanned customer interruptions - exc major incidents | No. of customers affected | Comparator | 6388
| % per number of total customers | Comparator | 0.3299%
| Average duration in minutes | Comparator | 734.2814
Number of major incidents | Number : Customers Effected | Comparator | 0 : 0
Customer Satisfaction
Customer Satisfaction - unplanned interruptions | score out of 10 | Ofgem target (8.01) | 9.2715
Customer Satisfaction - planned interruptions | score out of 10 | Ofgem target (8.04) | 7.7966
Customer Satisfaction - connections | score out of 10 | Ofgem target (8.09) | 7.6923
Complaints metric | scoring of complaints resolution | Ofgem target - need to be below 11.57 | 10.1988
Connections
% of all quotes issued within timescales set | % | Ofgem target | 99.75%
% of jobs substantially completed on date agreed with the customer | % | Ofgem target | 91.4%
Social Obligations
Fuel Poor Connections made in year | No. | Ofgem target | 1112
% of fuel poor connections RIIO to date vs period to date target | % better than target | Comparator | 2.196%
Safety
Attend Uncontrolled escape in 1 hr | % achieved | Ofgem target is 97% | 98.45%
Attend Controlled escape in 2 hrs | % achieved | Ofgem target is 97% | 99.11%
Annual repair risk performance vs target | % better than target | Ofgem target | 84.5%
Iron mains risk removed | % better than target | Ofgem target | 110.6%
Environmental Impact
Reduction in shrinkage in year (gas emmissions) | Volume (GWh) | Comparator | -5.8191
Shrinkage actuals compared to target volume | Improved shrinkage % | Ofgem target | 5.852%
Renewable gas connections | Number : Volume (scmh) | Comparator | 3 : 1400
Financials
Totex operating costs | £m | Ofgem Target | 171.7579
% lower Totex than allowance | % | Comparator | 8.854%
Other pass through costs | £m | Comparator | 62.5224