## Construction Plan
GT Reference | UIP Name | Team Leader | Contact Number | TL EUSR No. | Site Location | Developer Name | Work Type | Pipe Size | Pressure Tier | NRSWA Notice | SCO Permit | Phase of Operation | Chainage | Start Date | Finish Date | Comments
110011111 | Joe Bloggs Ltd | Joe Blogs | 07771234567 | 111111 | 35 Acacia Avenue, Hinckley, LE10 0NA | Joe Bloggs Construction | Mains & Services | 180 PE | LP | XXXXXXX | RO/123456 | Excavation | 0-100 | 2021-01-01 | 2020-01-04
110011111 | Joe Bloggs Ltd | Joe Blogs | 07771234567 | 111111 | 35 Acacia Avenue, Hinckley, LE10 0NA | Joe Bloggs Construction | Mains & Services | 180 PE | LP | XXXXXXX | RO/123456 | Install 180 PE Pipe | 0-100 | 2021-01-05 | 2020-01-06
110011111 | Joe Bloggs Ltd | Joe Blogs | 07771234567 | 111111 | 35 Acacia Avenue, Hinckley, LE10 0NA | Joe Bloggs Construction | Mains & Services | 180 PE | LP | XXXXXXX | RO/123456 | Backfill and Reinstate | 0-100 | 2020-01-07 | 2020-01-09
110011111 | Joe Bloggs Ltd | Joe Blogs | 07771234567 | 111111 | 35 Acacia Avenue, Hinckley, LE10 0NA | Joe Bloggs Construction | Mains & Services | 180 PE | LP | XXXXXXX | RO/123456 | Excavation | 100-200 | 2020-01-09 | 2020-01-12
110011111 | Joe Bloggs Ltd | Joe Blogs | 07771234567 | 111111 | 35 Acacia Avenue, Hinckley, LE10 0NA | Joe Bloggs Construction | Mains & Services | 180 PE | LP | XXXXXXX | RO/123456 | Install 180 PE Pipe | 100-200 | 2020-01-13 | 2020-01-14
110011111 | Joe Bloggs Ltd | Joe Blogs | 07771234567 | 111111 | 35 Acacia Avenue, Hinckley, LE10 0NA | Joe Bloggs Construction | Mains & Services | 180 PE | LP | XXXXXXX | RO/123456 | Install 63PE Service | Service 1 | 2020-01-14 | 2020-01-14
110011111 | Joe Bloggs Ltd | Joe Blogs | 07771234567 | 111111 | 35 Acacia Avenue, Hinckley, LE10 0NA | Joe Bloggs Construction | Mains & Services | 180 PE | LP | XXXXXXX | RO/123456 | Backfill and Reinstate | 100-200 | 2020-01-15 | 2020-01-17
110011111 | Joe Bloggs Ltd | Joe Blogs | 07771234567 | 111111 | 35 Acacia Avenue, Hinckley, LE10 0NA | Joe Bloggs Construction | Mains & Services | 180 PE | LP | XXXXXXX | RO/123456 | Pneumatic Strength & Tightness Test | 0-200 & Service 1 | 2020-01-18 | 2020-01-18
110011111 | Joe Bloggs Ltd | Joe Blogs | 07771234567 | 111111 | 35 Acacia Avenue, Hinckley, LE10 0NA | Joe Bloggs Construction | Mains & Services | 180 PE | LP | XXXXXXX | RO/123456 | Commissioning | 0-200 & Service 1 | 2020-01-18 | 2020-01-18